## Sheet1
S.No | Task Description | Mayur | Mason
1 | Literature Survey
2 | Problem articulation
3 | Solution Design
4 | Data Collection
5 | Coding and unit testing
6 | System Testing
7 | Documentation of Results
8 | Project Report

## Sheet2
Task | Start Date | End Date | Duration
Literature Survey | 2021-11-15 | 2021-11-20 | 5
Problem articulation | 2021-11-20 | 2021-11-23 | 3
Data Collection | 2021-11-23 | 2021-12-01 | 8
Expert Analysis | 2021-11-24 | 2021-12-04 | 10
Solution Flow Design | 2021-12-02 | 2021-12-04 | 2 | 44515
Data Set Creation | 2021-12-04 | 2021-12-06 | 2 | 44540
Model Building | 2021-12-05 | 2021-12-07 | 2
Model Testing | 2021-12-06 | 2021-12-07 | 1
Comparison of Results | 2021-12-07 | 2021-12-08 | 1
Documentation of Results | 2021-12-08 | 2021-12-09 | 1
Project Report | 2021-12-09 | 2021-12-10 | 1